## Sheet1
Project Plan
DEADLINE: MAY 13, 2025 | [5 empty] | Days Left: 47 days |  |  |  | Task Done: 6 / 33
Task ID | Task Name | Sub Task ID | SubTask Name | Deliverables | Assignee | Estimated Hours (days) | Pln St Date | Act StDate Started | Pln End Date | Act End Date | Status
R01 | Project Initiation | R01.1 | Define project objectives | Project scope document | Charmaine Valenzona | 1 | 2025-03-21 | 03/21/2025 | 03/21/2025 | 03/21/2025 | Done
|  | R01.2 | Project closure & documentation | Stakeholder list | Lowee Jay T. Perez | 1 | 2025-03-22 | 03/22/2025 | 03/22/2025 | 03/22/2025 | Done
|  | R01.3 | Conduct feasibility study | Feasibility report | Nicoleen S. Magwangay | 1 | 2025-03-23 | 03/23/2025 | 03/23/2025 | 03/23/2025 | Done
|  | R01.4 | Create project plan | Project plan document | Charmaine Valenzona | 1 | 2025-03-24 | 03/24/2025 | 03/24/2025 | 03/24/2025 | Done
|  | R01.5 | Obtain approvals | Approved project charter | Lowee Jay T. Perez | 1 | 2025-03-25 | 03/25/2025 | 03/25/2025 | 03/25/2025 | Done
R02 | Requirement Analysis | R02.1 | Gather functional requirements | Requirement specification document | Charmaine Valenzona | 1 | 2025-03-26 | 03/26/2025 | 03/26/2025 | 03/26/2025 | Done
|  | R02.2 | Gather non-functional requirements | Performance & security requirements | Charmaine Valenzona | 1 | 2025-03-27 | 03/28/2025 | 03/28/2025 |  | Ongoing
|  | R02.3 | Define system architecture | System architecture diagram | Nicoleen S. Magwangay | 2 | 2025-03-28 | 03/28/2025 | 03/29/2025 |  | Ongoing
|  | R02.4 | Create wireframes/mockups | UI wireframes | Lowee Jay T. Perez | 2 | 2025-03-30 | 03/30/2025 | 03/31/2025 |  | Ongoing
R03 | Design Phase | R03.1 | Database design | ERD and database schema | Nicoleen S. Magwangay | 3 | 2025-04-01 |  |  |  | Pending
|  | R03.2 | API design | API documentation | Charmaine Valenzona | 2 | 2025-04-04 |  |  |  | Pending
|  | R03.3 | UI/UX design | Final UI/UX designs | Lowee Jay T. Perez | 2 | 2025-04-06 |  |  |  | Pending
|  | R03.4 | Security design | Security measures document | Lowee Jay T. Perez | 4 | 2025-04-08 |  |  |  | Pending
R04 | Development Phase | R04.1 | Set up development environment | Configured development tools | Nicoleen S. Magwangay | 1 | 2025-04-12 |  |  |  | Pending
|  | R04.2 | Frontend development (React Native) | Initial UI screens | Charmaine Valenzona | 3 | 2025-04-13 |  |  |  | Pending
|  | R04.3 | Backend development | Working backend APIs | Lowee Jay T. Perez | 5 | 2025-04-16 |  |  |  | Pending
|  | R04.4 | QR Code scanning implementation | Functional QR scanner module | Charmaine Valenzona | 2 | 2025-04-21 |  |  |  | Pending
|  | R04.5 | GPS validation implementation | Functional GPS validation | Nicoleen S. Magwangay | 3 | 2025-04-23 |  |  |  | Pending
|  | R04.6 | Secure storage implementation | Encrypted storage module | Lowee Jay T. Perez | 2 | 2025-04-26 |  |  |  | Pending
|  | R04.7 | Testing unit integration | Test reports | Charmaine Valenzona | 1 | 2025-04-28 |  |  |  | Pending
R05 | Testing and Q&A | R05.1 | Functional testing | Test case reports | Nicoleen S. Magwangay | 1 | 2025-04-29 |  |  |  | Pending
|  | R05.2 | Security testing | Security vulnerability report | Charmaine Valenzona | 1 | 2025-04-30 |  |  |  | Pending
|  | R05.3 | User acceptance testing | User feedback & approval | Lowee Jay T. Perez | 1 | 2025-05-01 |  |  |  | Pending
R06 | Deployment | R06.1 | Prepare deployment environment | Deployment guide | Charmaine Valenzona | 1 | 2025-05-02 |  |  |  | Pending
|  | R06.2 | Deploy backend API | Hosted backend | Lowee Jay T. Perez | 2 | 2025-05-03 |  |  |  | Pending
|  | R06.3 | Deploy mobile app (beta) | Beta version released | Nicoleen S. Magwangay | 1 | 2025-05-05 |  |  |  | Pending
|  | R06.4 | Fix deployment issues | Issue resolution report | Lowee Jay T. Perez | 3 | 2025-05-06 |  |  |  | Pending
|  | R06.5 | Release final version | Live mobile app | Nicoleen S. Magwangay | 1 | 2025-05-09 |  |  |  | Pending
R07 | Test-Driven Development (TDD) | R07.1 | Prepare presentation materials | Test Cases, Unit Tests TDD Implementation | Charmaine Valenzona | 1 | 2025-05-10 |  |  |  | Pending
|  | R07.2 | Conduct demo for stakeholders | Presentation slides | Lowee Jay T. Perez | 1 | 2025-05-11 |  |  |  | Pending
|  | R07.3 | Gather final feedback | Live demonstration | Nicoleen S. Magwangay | 1 | 2025-05-12 |  |  |  | Pending
|  | R07.4 | Project closure & documentation | Feedback report | Charmaine Valenzona | 1 | 2025-05-13 |  |  |  | Pending
Formulas:
Pln St Date = [Pln St Date, row above]+[Estimated Hours (days), row above]